## CRS
Comment ID | Document Number | Revision | Section / Sheet Ref | Comment | Category | Criticality | Raised By | Date Raised | Author Response | Response Code | Status | Closed By / Date
C-042 | DWG-ME-1204 | Rev B | §4.2 / Sheet 3, Detail A | Pipe support spacing exceeds allowable span per spec 200-PIP-001 | Technical | High | J. Weber (Piping) | 2026-07-03 | Support spacing revised to 3.0 m; see Rev C | Accepted | Closed | J. Weber, 2026-07-15
C-043 | DWG-ME-1204 | Rev B | Title block | Drawing title does not match the document register entry | Editorial | Low | A. Silva (Doc Control) | 2026-07-03 | Title corrected to match register | Accepted | Answered
C-044 | SPC-PR-0088 | Rev A | §7.1 | Section does not state the design pressure; add it per datasheet DS-1104 | Technical | Medium | M. Okafor (Process) | 2026-07-04 |  |  | Open

## Status Codes
Status | Meaning | Who Moves It Forward
Open | Comment raised, no response yet | Author
Answered | Author has responded, awaiting reviewer verification | Reviewer
In Discussion | Response disputed; needs a decision | Lead / Consolidator
Closed | Reviewer confirmed the resolution in the revised document | Nobody — closed is final

## How To Use
# | Ground Rule | Why It Matters
1 | One comment per row. | Compound comments can be half-resolved, and half-resolved comments are the seeds of claims. Split them.
2 | Only the reviewer closes a comment. | The author answering is not the same as the comment being resolved. If authors close their own comments, the audit trail proves nothing.
3 | The Comment ID is sacred. | IDs never change between revisions. When Rev C is issued, C-042 must still be C-042, or cross-revision traceability dies.
4 | Write comments as verifiable requirements. | "Section 4 is unclear" cannot be closed objectively. "Section 4 does not state the design pressure; add it per DS-1104" can.
5 | One sheet, one owner. | A designated consolidator merges reviewer input. Two people editing parallel copies means two conflicting records.